## Sheet1
Project | TCO - Spring Cloud Stream binder for IBM MQ
Review ID | 375035
Review Type | Aggregation
Author | iRabbit
Submission | 229558
Name | Description | Reviewer | Response Type | Status | FF Status
Group 1 | General Assembly
Section 1.1 | Functional Requirements
Question 1.1.1 | Each major requirement is implemented correctly as specified in the contest specification.
Question 1.1.2 | Each minor requirement was implemented correctly as specified in the contest specification.
Reviewer Response 1 | From spec: "The IBM MQ binder should address the following aspects/features specifically in relation to IBM MQ: Transactionality (both local and distributed (XA)". -- But the only code related to transactions you have is setting the transacted flag when you initialize the listener container: final AbstractMessageListenerContainer listenerContainer = new DefaultMessageListenerContainer(); listenerContainer.setConnectionFactory(ibmMqConnectionManager.getJmsConnectionFactory()); listenerContainer.setDestinationName(name.toUpperCase()); listenerContainer.afterPropertiesSet(); listenerContainer.setReplyPubSubDomain(useTopic); listenerContainer.setPubSubDomain(useTopic); listenerContainer.setSessionTransacted(consumerProperties.isTransacted()); ////////////////////// set transacted flag listenerContainer.afterPropertiesSet(); -- Based on the Spring docs, this only relates to local transactions, not distributed (XA) ones. See section 30.4.5, "Processing messages within transactions": http://docs.spring.io/spring/docs/current/spring-framework-reference/html/jms.html#jms-tx-participation -- To include the listener container in a distributed transaction, you need to set a JtaTransactionManager on the listener container as shown in the example from the Spring docs, but you don't support this. | wcheung | Required | Accepted | added a new configuration for a pluggable TransactionManager to IbmMqConsumerProperties, That can be used to configure the JtaTransactionManager with the binder
Question 1.1.3 | Does the application handle erroneous input gracefully?
Section 1.2 | Nonfunctional Requirements
Question 1.2.1 | Can the application be deployed easily, without complications or troubleshooting, in the development environment? Is automation used effectively? If automation is not required, is there enough separation in how the build or shell scripts are written to make automated deployment easier in future?
Reviewer Response 1 | I followed this instruction from your DG: === 2. Navigate to ```docker``` folder of the submission and build the custom docker image ```docker build -t mq-for-binder .``` === -- But I get error: $ docker build -t mq-for-binder . Sending build context to Docker daemon 3.072 kB Step 1 : FROM mq Pulling repository docker.io/library/mq Error: image library/mq not found -- To fix I had to edit your Dockerfile and change: FROM mq -- to: FROM ibmcom/mq:8 -- which is the version of the mq image I pulled down from Docker hub based on spec and forum. | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | Why do we need this manual step: === 1. Extract the native MQ java library from docker container first navigate to lib/ directory, then run the following command ```docker cp ibmmq-for-binder:/opt/mqm/java/lib/com.ibm.mq.allclient.jar ./``` === -- Why don't you just provide this jar in your submission so future developers don't need to set up the Docker container just to build your code. The Docker container is only needed for verification, not for build. | wcheung | Required | Accepted | Added the allclient.jar file to submission
Appeal | Hi wcheung, Thanks for your review 1. The problem is that IBM just published mq image in the docker hub (during submission), My submission followed the procedure in the github to manually install the base mq image from github repo. a reference to the guide is added to the step 1 in the setup procedure 2. I remember I read that we can't distribute those jars in any format (can't catch the source now) |  | Appeal
Appeal Response | RE #1: It was posted in the forum on Thu, Jul 21, 2016 at 9:30 AM EDT which was more than 4 days before submission ended (07.25.2016 15:20 EDT). -- see https://apps.topcoder.com/forums//?module=Thread&threadID=888476&start=0 All participants are expected to monitor the forum so you should have updated your Dockerfile based on the update. RE #2: During the review I went through the references in the spec and the forum and I didn't see a limitation like that. Since you can't provide the reference now, I can't accept your appeal. Also, the spec said: "To support dynamic binder mapping (automatically creating new topics) the use of the native MQ libraries will probably be needed (can be supplied on demand)." -- So the client said the native libraries can be supplied on demand, which clearly means you could have asked for them and included them in your submission. -- I appreciate your thanks for my review. | wcheung | Appeal Response
Reviewer Response 1 | missing required steps 1. docker pull ibmcom/mq instead of docker pull mq | iRabbit | Required | Accepted | Fixed
Reviewer Response 2 | 2. spring-cloud-stream needs to be installed first.the snapshot version can't be retrieved from maven repo | iRabbit | Required | Accepted | Instructions added to use the maven "spring" profile which points to the required repository to fetsh snapshot versions
Question 1.2.2 | Does the implementation include all required dependencies to ensure that the application can be deployed successfully in the TARGET environment used by the client? For example, if the module will be used inside a container, it must deploy successfully in that container in addition to the possibly different environment used for development.
Question 1.2.3 | Does the application stay usable under various edge cases?
Question 1.2.4 | Is the application responsive? Do user actions complete in an appropriate amount of time?
Question 1.2.5 | Are all application data secure? If there are data entitlement constraints regarding retrieval, display and persistence of data, verify that these constraints are met in the submission.
Group 2 | Module Assembly
Section 2.1 | Design Adherence
Question 2.1.1 | The implementation uses all required technologies (language, framework, etc) and packages as specified in the requirement and design documents. Best practices for the technology are followed unless specified otherwise.
Question 2.1.2 | The implementation properly implements configurable parameters as defined in the design documents. Ensure that the implementation uses an appropriate level of configurability to facilitate future expansion with a minimum of code change.
Section 2.2 | Code Review
Question 2.2.1 | For those parts that are not covered by the design documents (architecture) the assemblers must properly adhere to basic design principles. The code must be ready to accommodate foreseeable and likely change requests. This usually refers to the utility classes, helper logic, etc. that the assemblers produce out of the architecture scope.
Reviewer Response 1 | These inner classes should be static since don't depend on their outer class: private class JmsMessageDrivenChannelAdapter extends JmsMessageDrivenEndpoint implements MessageProducer { public class Params implements BasePcfCommand.Params { public class Params implements Command.Params { | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | Private logger should be static: public abstract class BasePcfCommand<t p extends basepcfcommand.params> implements Command<t p> { private final Log logger = LogFactory.getLog(this.getClass());</t></t> | wcheung | Required | Accepted | It is initialized with (this.getClass()), so can't be static
Reviewer Response 3 | Instance variable `code` below should be final: private int code; MessageCompressionTechnique(final int code) { this.code = code; } public int getCode() { return code; } | wcheung | Recommended | Accepted | Fixed
Reviewer Response 4 | Why do you call afterPropertiesSet twice: final AbstractMessageListenerContainer listenerContainer = new DefaultMessageListenerContainer(); listenerContainer.setConnectionFactory(ibmMqConnectionManager.getJmsConnectionFactory()); listenerContainer.setDestinationName(name.toUpperCase()); listenerContainer.afterPropertiesSet(); ////////////////////// 1 listenerContainer.setReplyPubSubDomain(useTopic); listenerContainer.setPubSubDomain(useTopic); listenerContainer.setSessionTransacted(consumerProperties.isTransacted()); listenerContainer.afterPropertiesSet(); ////////////////////// 2 -- It should only be called once after the properties are set for validation. | wcheung | Required | Accepted | Fixed
Reviewer Response 5 | From spec: "The project structure should follow the standard set out in the reference binders". -- The Rabbit binder has a spring.provides file in src/main/resources/META-INF/ but you don't. | wcheung | Required | Accepted | the submission contains the file META-INF/spring.binders Which what is required to fetch the binder implementation
Question 2.2.2 | The implementation chooses efficient ways to perform the functional tasks.
Question 2.2.3 | There is no unnecessary or careless object instantiation or variable assignment.
Reviewer Response 1 | What's the purpose for having the spring-cloud-stream-binder-ibmmq-test-support project? It's empty (except for a pom.xml file). | wcheung | Required | Accepted
Reviewer Response 2 | Should define a property for MQ library version in parent pom.xml instead of repeating 8.0.0.4: <dependency> <groupid>com.ibm</groupid> <artifactid>com.ibm.mq.allclient</artifactid> <version>8.0.0.4</version> </dependency> <dependency> <groupid>com.ibm</groupid> <artifactid>com.ibm.mq.pcf</artifactid> <version>8.0.0.4</version> </dependency> | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | You have a property defined for the Spring library version so should use it instead of specifying "4.3.0.RELEASE" again: <dependency> <groupid>org.springframework.integration</groupid> <artifactid>spring-integration-jms</artifactid> <version>4.3.0.RELEASE</version> </dependency> | wcheung | Required | Accepted | Fixed
Reviewer Response 4 | Test dependencies in parent pom.xml should have test scope since they should never be included in a built artifact: <dependency> <groupid>org.mockito</groupid> <artifactid>mockito-all</artifactid> <version>1.10.19</version> </dependency> <dependency> <groupid>org.hamcrest</groupid> <artifactid>hamcrest-all</artifactid> <version>1.3</version> </dependency> | wcheung | Required | Accepted | Fixed
Question 2.2.4 | Errors must be properly encapsulated from the end user, who should not see a straight stack trace or logging intended for the developer or the support team. Error message must be appropriate so that user knows how to react, and can properly engage administrators or a support team to reproduce and diagnose the problem.
Question 2.2.5 | Application must produce the proper logs for the administrators to utilize. Reviewer should not only examine whether appropriate logging messages are produced, but should also check if the right logging levels are used.
Reviewer Response 1 | For: this.logger.error("Error", e); -- instead of "Error" why not use e.getMessage() or a specific message to be more useful? | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | How is using "Error" for the error message useful when you have an exception: } catch (MQException e) { throw new IbmMqException("Error", e); } | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | Shouldn't be a confusing ": " in the error message: } catch (MQException e) { throw new IbmMqException("Error: ", e); } | wcheung | Required | Accepted | Fixed
Reviewer Response 4 | In this method: @Override protected MessageProducer createConsumerEndpoint(... -- why don't you log any exception like you do in other methods in the class: } catch (final IbmMqException e) { throw new RuntimeException(e); } | wcheung | Required | Accepted | Fixed
Question 2.2.6 | Application must adhere to the proper transaction level as specified by the design documents.
Question 2.2.7 | Application must protect against malicious or potentially unsafe code.
Question 2.2.8 | There is no duplication of code observed in the implementation, including code written for automated tests. Code is appropriately refactored to eliminate redundancy.
Question 2.2.9 | The implementation code contains detailed and useful documentation.
Reviewer Response 1 | Most of your classes don't have class-level javadoc describing their purpose, let alone method-level javadoc. | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | Javadoc doesn't match code: * @throws IbmMqException wraps any IBM error. ... } catch (final IbmMqException e) { throw new RuntimeException(e); } | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | Should add comment these are default values: public class IbmMqProperties { private String host = "127.0.0.1"; private Integer port = 1414; private String qm = "QM1"; private String channel = "SYSTEM.DEF.SVRCONN"; private Integer maxQueueDepth = 100000; | wcheung | Required | Accepted | Fixed
Reviewer Response 4 | Should add comment why you use empty string as topicName and topic name as topicObject: return ibmMqNativeClient.getQueueManager().accessTopic("", params.getTopicName(), | wcheung | Required | Accepted | Fixed
Reviewer Response 1 | missing documentation for many classes and methods | iRabbit | Comment | Rejected
Question 2.2.10 | All code, including test cases, follows the TopCoder coding conventions as documented in the General Assembly Tutorial.
Reviewer Response 1 | From spec: "The source code should pass our Checkstyle checks". But it doesn't pass: [INFO] There are 24 errors reported by Checkstyle 6.19 with checks.xml ruleset. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqBaseChannelProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqBinderConfigurationProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqBindingProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqConsumerProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqExtendedBindingProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqMessageChannelBinderConfiguration.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\config\IbmMqProducerProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\DestinationType.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\cloud\stream\binder\ibmmq\IbmMqMessageChannelBinder.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\BasePcfCommand.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\Command.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\CommandParam.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\CreateQueueCommand.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\CreateTopicCommand.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\InquireQueueCommand.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\commands\InquireTopicCommand.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\HeaderCompressionTechnique.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\IbmMqAdmin.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\IbmMqConnectionManager.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\IbmMqNativeClient.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\IbmMqProperties.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\MessageCompressionTechnique.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\admin\PCFMessageAgentManager.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [ERROR] src\main\java\za\co\absa\ibmmq\IbmMqException.java:[0] (misc) NewlineAtEndOfFile: File does not end with a newline. [INFO] ------------------------------------------------------------------------ [INFO] Reactor Summary: [INFO] [INFO] spring-cloud-stream-binder-ibmmq-parent ............ SUCCESS [ 15.462 s] [INFO] spring-cloud-stream-binder-ibmmq ................... FAILURE [01:03 min] [INFO] spring-cloud-starter-stream-ibmmq .................. SKIPPED ... | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | Since this is Assembly, should add standard TopCoder copyright headers, etc. It's inconsistent you add author/version tags only for some classes. | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | Inconsistent to use your name in the javadoc here only: /** * Created by ahmed on 7/23/16. */ public class PCFMessageAgentManager { } | wcheung | Required | Accepted | Fixed
Reviewer Response 4 | From forum, package name should be: com.ibm.mp.springcloud.stream.binder -- see https://apps.topcoder.com/forums//?module=Thread&threadID=888369&start=0 But you use: za.co.absa.cloud.stream.binder.ibmmq | wcheung | Required | Accepted | Confirmed to use the current
Reviewer Response 5 | Should put space after colon: throw new IbmMqException("PCF Command Failed: Reason Code:" + res[0].getReason()); | wcheung | Required | Accepted | Fixed
Section 2.3 | Automated Tests
Question 2.3.1 | Automated tests such as unit test cases thoroughly test all methods and constructors.
Reviewer Response 1 | From spec: "There should be a full complement of unit and integration tests for the binder implementation". -- But you only have one unit test, which is for the IbmMqAdmin class and not any other classes, including binder-level classes. Note the Rating 1 description: "Rating 1 - Some of the core methods or constructors are not tested." | wcheung | Required | Accepted | Tests added to handle all possible configuraiton scenarios
Reviewer Response 2 | Why is this test empty: @Test public void testGetOrCreateTopic_notExists() throws Exception { } | wcheung | Required | Accepted | Fixed
Question 2.3.2 | Test cases effectively test the implementation.
Reviewer Response 1 | Should provide automated tests which verify the requirements are actually implemented: - Mapping to existing queues or topics - Automatically creating (based on binding destination name) non existent topics - MQ header functionality - Authentication and encrypted transport layer support The spec also says regarding the tests: "See the reference binders for examples". - Look at the RabbitMQ binder and you see multiple unit and integration tests: https://github.com/spring-cloud/spring-cloud-stream-binder-rabbit/tree/master/spring-cloud-stream-binder-rabbit/src/test/java/org/springframework/cloud/stream/binder/rabbit | wcheung | Required | Accepted | Fixed
Question 2.3.3 | Where applicable, unit test cases properly make use of setup and teardown methods to configure the test environment.
Question 2.3.4 | The test code contains documentation for classes, methods and variables.
Reviewer Response 1 | There's no documentation for anything in IbmMqAdminTest.java. | wcheung | Required | Accepted | Fixed
Section 2.4 | Test Data
Question 2.4.1 | The submission includes useful test data to verify the implementation works as designed.
Section 2.5 | Deployment Guide
Question 2.5.1 | Deployment guide is well written and details the steps to configure and deploy the application.
Reviewer Response 1 | Should document versions of Java and Maven required, even if specified in spec. DG should be complete. Errors result if older versions of either are used. | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | I followed this instruction from your DG: === 1. From the root submission directory, run ```mvn clean install``` === -- But I get error: [ERROR] The build could not read 1 project -> [Help 1] [ERROR] [ERROR] The project za.co.absa:spring-cloud-stream-binder-ibmmq-parent:1.0-SNAPSHOT (C:\Users\william\Downloads\Spring Cloud Stream binder for IBM MQ\submission-229558\pom.xml) has 1 error [ERROR] Non-resolvable import POM: Could not find artifact org.springframework.cloud:spring-cloud-stream-dependencies:pom:1.1.0.BUILD-SNAPSHOT @ line 28, column 25 -> [Help 2] -- When I search in https://mvnrepository.com for "spring-cloud-stream-dependencies", there is no version "1.1.0.BUILD-SNAPSHOT" in the public Maven repo. Here are the versions available: https://mvnrepository.com/artifact/org.springframework.cloud/spring-cloud-stream-dependencies -- Then I saw that in your parent pom.xml you have this repo defined: <repository> <id>spring-snapshots</id> <name>Spring Snapshots</name> <url>http://repo.spring.io/libs-snapshot-local</url> <snapshots> <enabled>true</enabled> </snapshots> <releases> <enabled>false</enabled> </releases> </repository> -- When I go to this repo online, I see it has the "1.1.0.BUILD-SNAPSHOT" version for the artifact: http://repo.spring.io/libs-snapshot-local/org/springframework/cloud/spring-cloud-stream-dependencies/1.1.0.BUILD-SNAPSHOT/ -- But because the repo is defined in a profile, it's not included by default: <profile> <id>spring</id> <repositories> <repository> <id>spring-snapshots</id> <name>Spring Snapshots</name> -- So your command is not correct: mvn clean install -- It should be: mvn clean install -P spring -- to activate the profile "spring" which has the repo defined for "1.1.0.BUILD-SNAPSHOT" of the artifact.</repository></repositories></profile> | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | There are Checkstyle violations that cause your build to fail as reported above. To skip them so I could build I had to run: mvn clean install -P spring -Dcheckstyle.skip=true | wcheung | Required | Accepted | Fixed
Reviewer Response 1 | refer to Q1.2.1 | iRabbit | Required | Accepted | Fixed
Question 2.5.2 | The deployment guide contains easy to follow verification steps to properly test the implementation.
Reviewer Response 1 | You say: 1. Install mq image following [This Guide](https://github.com/ibm-messaging/mq-docker) -- Should document which version (tag) of the image to use, 8 or 9. I pulled 8 since in the forum yhansraj said to use 8. -- see https://apps.topcoder.com/forums//?module=Thread&threadID=888476&start=0 | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | Instructions are confusing. You say: 2. Navigate to ```docker``` folder of the submission and build the custom docker image ```docker build -t mq-for-binder .``` -- then you say: 3. Build custom docker image https://github.com/ibm-messaging/mq-docker -- But in the previous step you just told us to build custom docker image from your submission, so why do we now need to follow the GitHub site to build another one? | wcheung | Required | Accepted | Fixed
Reviewer Response 3 | For running the Docker container you say: === 4. Run the following to start server ```docker --debug run --env LICENSE=accept --env MQ_QMGR_NAME=QM1 --volume /mnt/sda1/mq-binder:/var/mqm --name ibmmq-for-binder --detach mq-for-binder``` === -- But on Mac/Windows we need to map port 1414 to the MQ listener port in the Docker container so we can connect from our host. To do that, the command should be: ```docker --debug run --env LICENSE=accept --env MQ_QMGR_NAME=QM1 --volume /mnt/sda1/mq-binder:/var/mqm --name ibmmq-for-binder --publish 1414:1414 --detach mq-for-binder | wcheung | Required | Accepted | Fixed
Reviewer Response 4 | Also since you use /mnt/sda1 as the mapped volume from the Docker VM, you should mention we need to make sure we have space in that volume, else the container won't start and because you use --detach option, we won't know unless we check the ps status. I actually had no space in my /mnt/sda1 volume and experienced this issue which I had to resolve by removing all old containers I had in my Docker VM. | wcheung | Recommended | Accepted
Reviewer Response 5 | You tell us to run the demo-sender and demo-receiver but you didn't tell us we need to configure this first: spring.ibmmq.host=172.17.0.4 -- in application.properties in: demos/demo-sender/src/main/resources/ -- and: demos/demo-receiver/src/main/resources/ -- The IP address of my Docker machine is not 172.17.0.4 so I had to change this. | wcheung | Required | Accepted | Fixed
Reviewer Response 6 | You should provide verification steps, not just say: 4. Update the application.properties configuration and rerun the demos to test different scenarios like choosing from topics/queues ,...etc | wcheung | Required | Accepted | Fixed
Reviewer Response 7 | Should provide verification for this requirement: === Most, if not all, Spring Cloud Stream modules should work out of the box with the MQ binder For example, a Source, Processor and Sink application should be able to execute successfully using the MQ binder implementation === -- These aren't covered by your sender/receiver demo. | wcheung | Required | Accepted | Fixed
Question 2.5.3 | All assets are named clearly and appropriately.
Reviewer Response 1 | Numbering of instructions is confusing. In "IBM MQ Setup" section you have: 3. Update maximum open files settings -- then: 2. Navigate to ```docker``` folder of the submission and build the custom docker image -- Why does 2 follow 3? | wcheung | Required | Accepted | Fixed
Reviewer Response 2 | In "IBM MQ Setup" section why are all 3 steps numbered 1? | wcheung | Required | Accepted | Fixed
Question 2.5.4 | The submission uses only allowable file formats listed in the Assembly Tutorial.
Reviewer Response 1 | System Design.docx is corrupt, as reported by Word Mac 2011. | wcheung | Required | Accepted | Fixed
Question 2.5.5 | The submission is organized in the format recommended by the Assembly Tutorial.
Question 2.5.6 | The deployment guide does not contain inaccurate or redundant information.